## Sheet1
Requirements Traceability Matrix (RTM)
Requirement ID | Requirement Description (Business Requirement / User Story) | Design Element | Test Case ID(s) | Defect ID(s)
BR-001 | Customers must be able to register for an account. | Registration form | TC-001: Successful registration | DE-001: Registration form error
BR-002 | Customers must be able to log in to their accounts. | Login form | TC-002: Successful login | DE-002: Login form error (invalid credentials)
US-001 | As a customer, I want to browse products by category so I can easily find what I'm looking for. | Product category navigation | TC-003: Browse products by category | -
US-002 | As a customer, I want to view detailed product information including images, descriptions, and prices before making a purchase. | Product detail page | TC-004: View product details | DE-003: Missing product image
US-003 | As a customer, I want to add items to my shopping cart so I can purchase them later. | Shopping cart functionality | TC-005: Add item to cart | TC-006: Remove item from cart.
US-004 | As a customer, I want to checkout and pay for my order using a secure payment gateway. | Secure checkout process | TC-007: Successful checkout with credit card | TC-008: Checkout process with different payment methods
BR-003 | The website must display product availability in real-time. | Inventory management system integration | TC-009: Verify product availability | -
Defect Status Report for Amazon Website (Based on the RTM)
Defect ID | Description | Date Reported | Status | Assigned To | Resolution | Target Resolution Date
DE-001 | Registration form error (e.g., missing field validation) | 2024-03-05 | Open | Developer A | Under investigation | 2024-03-10
DE-002 | Login form error (e.g., invalid credentials message not clear) | 2024-03-07 | In Progress | Developer B | Fix implemented, testing in progress | 2024-03-09
DE-003 | Missing product image | 2024-03-06 | Fixed | QA Tester | Image added, functionality verified | 2024-03-07
DE-004 | Cannot add item to cart (e.g., functionality not working) | New | To be assigned | - | Awaiting further investigation | 2024-03-08